## 407
|  |  | 22.10.2018 28.10.2018 | 29.10.2018-04.11.2018 | 05.11.2018 11.11.2018 | 12.11.2018-18.11.2018 | 19.11.2018-25.11.2018 | 26.11.2018-02.12.2018 | 03.12.2018-09.12.2018 | 10.12.2018-16.12.2018 | 17.12.2018-23.12.2018 | 24.12.2018-30.12.2018
Start Date: 22/010/2018 |  |  | WEEK 1 | WEEK 2 | WEEK3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10
Documentation |  | week(1-5,7-10)
Literature Review | Team | bar: WEEK 1
Software Requirements Specification | Team | bar: WEEK 2 to WEEK 5
Software Design Description | Team | bar: WEEK 7 to WEEK 8
Project Report / Project Tracking Form | Team | bar: WEEK 9 to WEEK 10
Project Webpage |  | week(6,10)
Project Webpage design by using XML languages | Team | bar: WEEK 6; WEEK 10
Testing |  | week(7-10)
Test Data | Team | bar: WEEK 7 to WEEK 10
Reporting | Team | bar: WEEK 7 to WEEK 10

## 408
Digital storytelling on a virtual heritage museum with believable agents based on Turkish horror folklore |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12
Start Date: |  |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D1 | D2 | D3 | D4 | D5 | D6 | D7
Sprint 1: Game Components Design |  | 21 days
3D Modelling | Utku,Saygın | 12 days | bar: WEEK 1 D1 to WEEK 2 D5
UI Design | Saygın | 2 days | bar: WEEK 2 D6 to WEEK 2 D7
Coding | Team | 9 days | bar: WEEK 1 D6 to WEEK 2 D7
Test Plan Documentation | Oğulcan | 7 days | bar: WEEK 1 D1 to WEEK 1 D7
Unit Testing | Team | 2 days | bar: WEEK 3 D1 to WEEK 3 D2
Acceptence Testing | Team | 3 days | bar: WEEK 3 D3 to WEEK 3 D5
Deployment | Team | 1 day | bar: WEEK 3 D6
Agile Retrospective Meeting | Team | 1 day | bar: WEEK 3 D7
Sprint 2: Environment an d Believable Agents |  | 21 days
3D Modelling | Utku,Saygın | 5 days | bar: WEEK 4 D1 to WEEK 4 D5
Sound Effects and Animation | Oğulcan | 7 days | bar: WEEK 4 D1 to WEEK 4 D7
Coding | Team | 10 days | bar: WEEK 4 D4 to WEEK 5 D6
Unit Testing | Oğulcan | 1 days | bar: WEEK 5 D7
Acceptence Testing | Team | 2 days | bar: WEEK 6 D1 to WEEK 6 D2
Presentation & Demo | Team | 2 days | bar: WEEK 6 D3 to WEEK 6 D4
Documentation | Team | 1 day | bar: WEEK 6 D5
Deployment | Team | 1 day | bar: WEEK 6 D6
Agile Retrospective Meeting | Team | 1 day | bar: WEEK 6 D7
Sprint 3: Believability and Behaviors of Agents |  | 21 days
Coding | Utku,Saygın | 11 days | bar: WEEK 7 D1 to WEEK 8 D4
Sound Effects and Animation | Oğulcan | 11 days | bar: WEEK 7 D1 to WEEK 8 D4
Unit Testing | Team | 2 day | bar: WEEK 8 D5 to WEEK 8 D6
Acceptence Testing | Team | 2 day | bar: WEEK 8 D7 to WEEK 9 D1
System Testing | Team | 4 days | bar: WEEK 9 D2 to WEEK 9 D5
Deployment | Team | 1 day | bar: WEEK 9 D6
Agile Retrospective Meeting | Team | 1 day | bar: WEEK 9 D7
Sprint 4: Believability and Behaviors of Agents |  | 21 days
Unit Testing | Team | 2 day | bar: WEEK 10 D1 to WEEK 10 D2
Acceptence Testing | Team | 2 day | bar: WEEK 10 D3 to WEEK 10 D5
System Testing | Team | 4 days | bar: WEEK 10 D6 to WEEK 11 D2
Project Report |  | 3 day | bar: WEEK 11 D3 to WEEK 11 D5
Final Presentation |  | 4 days | bar: WEEK 11 D6 to WEEK 12 D2
Demo Preperations | Team | 3 days | bar: WEEK 12 D3 to WEEK 12 D5
Final Relase |  | 1 day | bar: WEEK 12 D6
Agile Retrospective Meeting | Team | 1 day | bar: WEEK 12 D7